## Sheet1
DevOps Training Schedule
ID | Title | Description | Date_Start | Date_End | Deliverable | Reference
1 | AWS VPC | Create a new VPC with multiple subnet 2 public, 2 private Create 1 NAT Gateway, 1 Internet Gateway Create a route public to Internet, and private to NAT Gateway | 2018-05-30 | 2018-05-31 | Show the NAT Instace and explain the flow Install AWS CLI on Personal PC and create VPC by AWS CLI | https://aws.amazon.com/what-is-cloud-computing/ https://aws.amazon.com/what-is-aws/ https://aws.amazon.com/vpc/ https://docs.aws.amazon.com/cli/latest/reference/ec2/create-vpc.html
2 | AWS EC2 | Build an EC2 with AMI Attach a new volume Take snapshot volume Restore volume Bootup an EC2 with user-data script | 2018-06-01 | 2018-06-04 | Show EC2 and login by certificate Show process to take snapshot and restore Install AWS CLI on Personal PC and do the task by AWS CLI | https://aws.amazon.com/ec2/ https://docs.aws.amazon.com/cli/latest/reference/ec2/
3 | AWS Internet Infrastructure | Boot up 4 instances, 2 instances belong to Public Subnet, 2 instance belong to private subnet. Make sure it can access to internet | 2018-06-05 | 2018-06-05 | Show the internet access of Instances Understanding AWS SDK using Python boto3, Run the tasks with AWS SDK Python 3 | https://docs.aws.amazon.com/AmazonVPC/latest/UserGuide/VPC_Internet_Gateway.html https://docs.aws.amazon.com/AmazonVPC/latest/UserGuide/vpc-nat-gateway.html https://aws.amazon.com/sdk-for-python/
4 | AWS ELB | Install apache on 2 instances on private subnet Apply ELB to load balancing Apache on two instances AWS Auto Scale Instance | 2018-06-06 | 2018-06-06 | Show the instance had been access by log or $HTTP_SERVER variable Understanding AWS SDK using Python boto3, Run the tasks with AWS SDK Python 3 | https://aws.amazon.com/elasticloadbalancing/ https://aws.amazon.com/sdk-for-python/
5 | AWS S3 | Build a sample mini site static host on S3 with custom free domain (tribeatplus.xyz, blah blah) | 2018-06-07 | 2018-06-08 | Show the log S3 access static understand S3 bucket policy Understanding AWS SDK using Python boto3, Run the tasks with AWS SDK Python 3 | https://aws.amazon.com/documentation/s3/
6 | AWS Cloudfront | Continue #4 replace static S3 with Cloudfront Understanding the invalidate process | 2018-06-11 | 2018-06-11 | Show the log for access cloudfront Understanding AWS SDK using Python boto3, Run the tasks with AWS SDK Python 3 | https://aws.amazon.com/cloudfront/
7 | AWS Route53 | Replace DNS Register transfer to Route53, make sure the ELB will access by Route53 | 2018-06-12 | 2018-06-12 | Show domain http Understanding AWS SDK using Python boto3, Run the tasks with AWS SDK Python 3 | https://aws.amazon.com/route53/
8 | AWS RDS (Mysql, Postgres, SQL Server) | Replace Item#3 with a wordpress connect to RDS WordPress using S3 and Cloudfront Plugin | 2018-06-13 | 2018-06-14 | Show the dynamic site and explain the flow Understanding AWS SDK using Python boto3, Run the tasks with AWS SDK Python 3 | https://aws.amazon.com/rds/
9 | API Gateway | Learn how to implement API Gateway via AWS How website hook API Gateway via HTTP method (GET, POST, PUT ...) Implement a sample API Server which was access via API Gateway | 2018-06-15 | 2018-06-18 | Build sample REST API call site follow document | http://docs.aws.amazon.com/apigateway/latest/developerguide/api-gateway-create-api-from-example.html
10 | Lambda | Investigate what lambda can do How API Gateway call Lambda function Learn Python, NodeJS for Lambda (focus to S3, Cloudfront Dynamodb SDK) Implement sample Lambda function to copy S3 object from a bucket to other bucket Implement sample Lambda function to create invalidate when an S3 object was upload by HTTP method PUT | 2018-06-19 | 2018-06-20 | Build sample site with dynamodb backend and REST API | http://docs.aws.amazon.com/lambda/latest/dg/with-s3-example.html http://docs.aws.amazon.com/AWSJavaScriptSDK/latest/AWS/CloudFront.html
11 | Dockers | Understanding Docker | 2018-06-21 | 2018-06-22 | Build a an image, upload to Docker, download to container | https://docs.docker.com/get-started/
12 | Dockers compose | Understand docker compose | 2018-06-23 | 2018-06-23 | Do a sample docker compose site | https://docs.docker.com/compose/
13 | Dockers Swarm | Understanding Docker Swarm, Docker Services | 2018-06-24 | 2018-06-24 | Build a an image, upload to Docker, download to container | https://docs.docker.com/get-started/part3/
14 | Kubenetes | Understanding Kubernetes, build a sample Kubernetes cluster on AWS and GCB | 2018-06-27 | 2018-06-29 | Build a sample Kubernetes | https://kubernetes.io/docs/tutorials/
15 | Ansible | Understand Ansible | 2018-06-30 | 2018-07-02 | Do the #4 by Ansible | https://www.ansible.com
16 | Terraform | Understand Terraform | 2018-07-03 | 2018-07-05 | Do the #5 by Terraform | https://www.terraform.io
17 | Microservices | Understanding microservices | 2018-07-06 | 2018-07-06 | Build a sample Microservices with Django Framework | http://www.django-rest-framework.org
18 | Final Project | Form submit -> Django -> copy to S3 -> Lambda -> invalidate -> Lambda insert to DynamoDB + need to Load balancer + Need auto scale + Deploy by Ansible or Terraform | 2018-07-07 | 2018-06-21 | Present to our team | No document at all, you must think about the flow :D